DIVISION OF AGING, ADULT AND BEHAVIORAL HEALTH SERVICES

QUARTERLY REPORT

DHS STATE INSTITUTIONAL SYSTEM BOARD

FY23 First Quarter

July – August – September 2022

ARKANSAS STATE HOSPITAL (ASH)

Forensic Unit Security New ASH (NASH) Side:

The project to install additional fencing for added security to prevent elopements at a cost of $28,566.25 was approved by the SIS Board at the April 8, 2020, meeting.  Division of Building Authority (DBA) approved this project, it is now in the final review phase prior to bid request.

Additional Adolescent Courtyard:

The project for a courtyard on the southeast side of the adolescent building, Unit D, with an approximate square footage of 30,000 at a cost of $246,749 was approved by the SIS Board at the April 8, 2020, meeting.  DBA has approved this project and is now in the final review phase prior to bid request.

Forensic Bathroom/Shower Tile Replacement:

The forensic unit patient bathrooms are in need of redo: Plumbing, Hardware, and Epoxy Flooring. The tile is chipping, and grout is holding odors.  The epoxy flooring is more durable and easier to clean.

UPDATE:  Architect’s new quote of $750k is for all 24 forensic unit bathrooms. This is pending 1DE funding availability. In the meantime, we continue to follow an alternative cleaning schedule and make temporary repairs as needed.

Unit D Door Replacement:

Over the years, the adolescent patients have destroyed 3 different styles of door sets.  We have finally found a door set that can withstand heavy abuse and would like to start replacing existing door sets for the adolescent units.  The average cost will be $22,000 per set.

UPDATE:  2 sets of doors have been replaced. There are 4 sets that still need replacing for a total estimated cost of $88,000.

Joint Commission (JC) Findings Related to Ligature Risks:

ASH was required to take immediate action because of recent JC survey and make the following corrections in effort to reduce ligature points:

- Replacement of all hinges in patient bedrooms, bathrooms, and group rooms with a continuous style hinge has been completed

- Replacement and additions of door closures for group and storage rooms connected to patient care areas has been completed. Cost for both 1 and 2 was $255,000

- Replacement of all HVAC ceiling grills in patient bedrooms, bathrooms, and day areas is complete. Cost of $80,870.

UPDATE:  JC surveyor returned to ASH in July to inspect work and the hospital passed in all areas and was released from all findings related to the ligature risks.

ARKANSAS HEALTH CENTER (AHC)

New Roofs for Building 80, Cottage 12, and Chapel:

At the October 13, 2021, meeting, the Board approved the roofing projects, requesting updates on project estimates.

Bldg. 80 - The roof estimate of $206,000 for Building 80 was submitted to Division of Building Authority (DBA) for review.  Building 80 came in over budget and is back in for review.  New budget $307,693.   Lowest bid came in at $329,704.00 from Mid-Ark Roofing, Inc.  They were awarded the bid and should start the project in the next four to five weeks.

Roof estimates for Cottage 12 and the Chapel were requested from Morris and Associates.

Cottage 12 - Eric Goins is obtaining bids for the roof of Cottage 12. A bid from Cornerstone Construction came in at $15,620.48.  No other bids have been received.

Chapel - The Chapel roof project was put out for bid.  Budget is now $110,000.00.  In addition to replacing the roof, this project includes repair of rotten facial board and painting of all wood.  Reynolds Construction and Commercial Roofing was the lowest bidder and was awarded the project at $108,227.00.

Building 80 Activity Room Addition:

At the July 8, 2020, meeting the Board approved requesting bids on the activity room addition project at an estimated cost of $300.000.  The updated estimated cost is $598,052, submitted to DBA for review.  Project is under review with no new updates.